## Gantt Chart
GANTT CHART TEMPLATE | [7 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | AI Eye
PROJECT MANAGER |  | Iris Huang | [5 empty] | DATE | [6 empty] | ##
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION |  | PCT OF TASK COMPLETE | PHASE ONE | [19 empty] | PHASE TWO | [14 empty] | PHASE THREE | [9 empty] | PHASE FOUR
[6 empty] | Days Left |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | T | W | R | F
1 | Project Conception and Initiation
1.1 | Model & Tool Research | Iris | 2021-01-21 | 2021-02-01 | 10 | -89 | 100% | bar: WEEK 1 M to WEEK 2 M
1.1.1 | Research and Setup Tool | All | 2021-02-01 | 2021-02-19 | 18 | -71 | 100% | bar: WEEK 2 M to WEEK 4 F
1.2 | System Design Document | All | 2021-02-01 | 2021-02-06 | 5 | -84 | 100% | bar: WEEK 2 M to WEEK 2 F
1.3 | Project Snapshot 1 | All | 2021-02-11 | 2021-02-21 | 10 | -69 | 100% | bar: WEEK 3 R to WEEK 4 F
1.4 | Setup Python Notebook | Iris | 2021-02-08 | 2021-02-21 | 13 | -69 | 100% | bar: WEEK 3 M to WEEK 4 F
2 | Train Custom datasets
2.1 | Train Ambulance Dataset | Iris | 2021-02-11 | 2021-02-25 | 14 | -65 | 100% | bar: WEEK 3 R to WEEK 5 R
2.2 | Download and Clean Datasets | Angela & Haya | 2021-02-18 | 2021-02-25 | 7 | -65 | 100% | bar: WEEK 4 R to WEEK 5 R
2.3.1 | Train Dataset#1 | Angela | 2021-02-21 | 2021-03-04 | 13 | -56 | 100% | bar: WEEK 6 R to WEEK 7 F
2.3.2 | Train Dataset#2 | Haya | 2021-02-27 | 2021-03-04 | 7 | -56 | 100% | bar: WEEK 7 M to WEEK 7 F
2.4 | Project Snapshot 2 | All | 2021-03-06 | 2021-03-07 | 1 | -53 | 100% | bar: WEEK 7 F
3 | Noise Image
3.1 | Test - Average Percision & Retrain | Iris | 2021-03-13 | 2021-03-25 | 12 | -35 | 100% | bar: WEEK 9 M to WEEK 9 F
3.1.1 | Research | Angela | 2021-03-08 | 2021-03-21 | 13 | -39 | 100% | bar: WEEK 8 M to WEEK 9 F
3.2 | Project Snapshot 3 | All | 2021-03-21 | 2021-03-21 | 0 | -39 | 100% | bar: WEEK 9 F
4 | Web Interface
3.2 | Poster | All | 2021-04-05 | 2021-04-09 | 4 | -21 | 100% | bar: WEEK 11 M to WEEK 11 R
5.1 | Design | Haya | 2021-04-05 | 2021-04-15 | 10 | -15 | 100% | bar: WEEK 10 M to WEEK 11 F
5.2 | Information & About Us Page | Haya & Angela | 2021-04-01 | 2021-04-22 | 21 | -8 | 100% | bar: WEEK 12 M to WEEK 12 T
5.3 | Access the model | Iris | 2021-04-20 | 2021-04-22 | 2 | -8 | 100% | bar: WEEK 12 M to WEEK 12 W
4.3 | Senior Project Day Oral Presentation | All | 2021-04-25 | 2021-04-30 | 5 | 0 | 100% | bar: WEEK 12 M to WEEK 12 F