## Gantt Chart
GANTT CHART TEMPLATE | [7 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | AI Eye
PROJECT MANAGER |  | Iris Huang | [5 empty] | DATE | [6 empty] | 2021-01-25
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION |  | PCT OF TASK COMPLETE | PHASE ONE | [19 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | Days Left |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Model & Tool Research | Iris | 2021-01-21 | 2021-02-01 | 10 | -20 | 100% | bar: WEEK 1 M to WEEK 2 M
1.1.1 | Research and Setup Tool | All | 2021-02-01 | 2021-02-19 | 18 | -2 | 100% | bar: WEEK 2 M to WEEK 4 F
1.2 | System Design Document | All | 2021-02-01 | 2021-02-06 | 5 | -15 | 100% | bar: WEEK 2 M to WEEK 2 F
1.3 | Project Snapshot 1 | All | 2021-02-11 | 2021-02-21 | 10 | 0 | 100% | bar: WEEK 3 R to WEEK 4 F
1.4 | Setup Python Notebook | Iris | 2021-02-08 | 2021-02-21 | 13 | 0 | 100% | bar: WEEK 3 M to WEEK 4 F
2 | Train Custom datasets
2.1 | Train Ambulance Dataset | Iris | 2021-02-11 | 2021-02-25 | 14 | 4 | 90% | bar: WEEK 3 R to WEEK 4 F; WEEK 5 R
2.2 | Download and Clean Datasets | Angela & Haya | 2021-02-18 | 2021-02-25 | 7 | 4 | 76% | bar: WEEK 4 R to WEEK 4 F; WEEK 5 R
2.3.1 | Train Dataset#1 | Angela |  | 2021-03-04 |  | 13 | 0%
2.3.2 | Train Dataset#2 | Haya |  | 2021-03-04 |  | 13 | 0%
2.3.3 | Train Dataset#3 | Iris |  | 2021-03-04 |  | 13 | 0%
2.5 | Project Snapshot 2 | All |  | 2021-03-07 |  | 16 | 0%
3 | Night Vision
3.1 | Research Night Vision |  |  | 2021-03-29 | 0 | 38 | 0%
3.1.1 | Obtain and Train dataset |  |  | 2021-03-29 | 0 | 38 | 0%
3.2 | Project Snapshot 3 |  |  | 2021-03-21 | 0 | 30 | 0%
3.3 | PURCC Abstract |  |  | 2021-04-02 | 0 | 41 | 0%
4 | Image Denoising with OpenCV
4.1 | Image Denoising with OpenCV |  |  | 2021-04-04 | 0 | 43 | 0%
4.1.1 | Obtain and Train dataset |  |  | 2021-04-04 | 0 | 43 | 0%
4.2 | Project Snapshot 4 |  |  | 2021-04-04 | 0 | 43 | 0%
4.3 | Poster |  |  | 2021-04-09 | 0 | 48 | 0%
5 | Web Interface(potential)
5.1 | Design |  |  | 2021-04-15 | 0 | 54 | 0%
5.2 | Information & About Us Page |  |  | 2021-04-22 | 0 | 61 | 0%
5.3 | Access the model |  |  | 2021-04-22 | 0 | 61 | 0%
4.3 | Senior Project Day Oral Presentation |  |  | 2021-04-30 | 0 | 69 | 0%
Formulas:
Days Left = DAYS360(TODAY(),[DUE DATE])